Basic Measures

Data Collection Workbook

Table of Contents

Introduction	3

Life Cycle Definition	3

Life Cycle Phase Semantics	4

Phase 1 – Feasibility Study (FEAS)	4

Phase 2 – Functional Design (FUNC)	5

Phase 3 – Main Build (MB)	5

Phase 4 – Maintenance (MAINT)	5

Notes on Maintenance and Non-Traditional Life Cycles	6

Throw-away Prototypes	6

Rapid-application Prototypes	6

Enhancements, Modifications, and Large-scale Maintenance	6

Software Sizing	7

Type Attribute	7

Origin Attribute	8

Usage Attribute	8

Description of Data	9

Basic Information	9

Project Information	9

Sizing	10

Defects	11

Time and Effort	11

Staffing Detail	13

Staffing – nth 12 Months	13

Application	14

Project Summary	14

Application Type	15

Predominant Development Machine	15

Predominant Operating System	15

Sizing	16

Function Unit Totals	16

Language Breakdown for Logical Source Statements (LSS)	17

Accounting	19

Effort	19

Labor Rate	20

Custom Fields	21

Environment	22

Summary Evaluation	22

Tooling and Methods Detailed Evaluation	24

Development System	24

Database Management System (DBMS)	25

Screen Writer	25

Report Writer	26

File Handling	26

Tool Capability / Use	27

Development Standards	29

Technical Difficulty Detailed Evaluation	31

Constraints	31

New Algorithms	32

New Logic	33

Complexity	33

Platform Stability	34

Personnel Profile Detailed Evaluation	36

Management / Leadership	36

Environment	37

Development Team	37

Reused, Unmodified Software Detailed Evaluation	39

Size	39

Complexity and Difficulty	40

Quality	43

Development Runtime Environment	43

Exposure	43

Defects from System Integration to Delivery	44

Operational Runtime Environment	44

Exposure	44

Reliability at Delivery	45

Defects After Delivery	45

Defect Discovery Detail	46

Defects – nth 12 Months	46

Review	47

Overruns / Slippages (by planned value)	47

Growth / Reduction (by planned value)	48

System Benefit/Effectiveness	48

Significant Factors	48

Data Collection Forms	49

# Introduction

Many development organizations today are looking for better ways to do business.  Measurement is an excellent mechanism for understanding the current capability of an organization and is the first step in any viable process improvement program.

Quantitative Software Management® (QSM®) performs Basic Measures, a basic entry-level productivity and quality measurement service for development organizations to help them get concrete results fast.

The objectives of this service are to:

- Establish a Measurement Baseline:  Collect and archive size, time, effort, reliability, and environment data on completed projects.

- Perform a Competitive Benchmark:  Show how the data compares to other similar organizations and projects.

- Identify Improvement Opportunities:  Identify potential areas for process improvement.

- Quantify Improvement Benefits:  Estimate the benefits of making those process improvements in terms of cycle time, cost, and quality.

- Determine Progress Since the Last Benchmark:  Where possible, compare the current benchmark to the last benchmark and quantify any change.

This workbook is designed to support the gathering of all data necessary to complete the Basic Measures objectives.  The sub-sections in this introduction provide guidance that is vital to reducing the amount of variability in the collected data.  Please read the entire introduction before entering any data.

The second major section of the workbook contains a description of the data items to be collected and analyzed using Quantitative Software Management's SLIM-Metrics® tool.  Each item requested corresponds to a data entry field in SLIM-Metrics®.

The last section of this workbook contains a camera-ready set of the actual data collection forms which are to be filled out (one set of forms for each project).

## Life Cycle Definition

It is very important, when filling out the data collection forms, to be consistent with QSM’s software life cycle phase definitions.  Figure 1 and the following sub-section provide definitions for each of these phases.

Figure 1  Software Resource Profile.  Graphic showing the application of people over time across 4 phases of development.

## Life Cycle Phase Semantics

### Phase 1 – Feasibility Study (FEAS)

The objectives of this phase are to develop a complete and technically feasible set of requirements for the system and to formulate the top level approach and plan for their implementation.  Typical products resulting from these activities include:  (1) a system specification, statement of need, or list of capabilities that the user or the marketing organization expects from the system, or a marketing specification;  (2) a feasibility study report or an assessment of whether the need can be met with the available technology in a timely and economic manner; and (3) a set of plans documenting the project management approach to development, quality assurance, configuration management, verification, etc.

This phase is complete when it is determined that building this system is feasible.  A system-level requirements review may be held at the completion of this phase to determine the scope of the effort and the approach for Phase 2.

### Phase 2 – Functional Design (FUNC)

The objectives of this phase are to complete the system-level design by choosing the appropriate constituent technologies (hardware, software, etc.) and to allocate each system-level requirement to the appropriate technology.  Software requirements are defined.  The software top-level architecture is defined.  Typical products include the following:  (1) specifications defining the interfaces between the system-level components; (2) software requirements specifications describing the inputs, processing (logic and/or algorithms), and outputs; and (3) updated project plans.

This phase is complete when all of its deliverables are approved.  A design review (e.g., PDR) may be held during this phase to baseline the system design, software requirements, and software top-level architecture.  Note that the Functional Design Phase normally overlaps the start of the Software Main Build Phase as the top-level software design is iterated and refined.

### Phase 3 – Main Build (MB)

Phase 3 seeks to implement the software requirements as defined in Phase 2.  Once the software requirements have been baselined, the activities in Phase 3 implement these requirements through software detail design, coding, and integration.  Typical products include:  (1) design documentation; (2) verification (inspection and/or test) procedures and results; (3) user manuals and other operating documentation; (4) maintenance manuals; (5) acceptance test procedures and reports; and (6) a full-functionality software product that has achieved at least 95% reliability and is acceptable for initial use in the customer’s environment.

This phase starts on the date when the very first module design is started.

This phase ends on the date when it is possible, for the first time, to deliver a full operational capability system with 95% of the total defects identified.  Subjectively, this is the point in the program where a full-functionality system can be delivered that has sufficient reliability so as not to be returned by the customer.

### Phase 4 – Maintenance (MAINT)

The objective of this phase is to provide the customer base with product support once the system is operational.  In some life cycles this phase includes continued testing to increase reliability and provide quality assurance to customers and certification authorities.  During this phase, latent corrections to residual bugs in the system are corrected.  The principle activities of this phase include:  (1) increased reliability and assurance testing; (2) correction of latent defects; and (3) minor modification and tuning of the system.

In some life cycles, this phase is complete when management decides that the system is no longer of practical use and cuts off additional resources.  Some time before this happens, management may seek more improvements and initiate a feasibility study for a new system to replace it.  In other life cycles, this phase is complete when some sort of certification occurs.  Evolution of the product beyond this point typically spawns new projects.

## Notes on Maintenance and Non-Traditional Life Cycles

When gathering project data, it is not essential that the product has been developed according to the life cycle in Figure 1.  Rather, the goal is to identify the development style and map its activities to one or more of these high level phases (with interim milestones depicted) which may be overlapped, staffed, and iterated in various ways.

Listed below are some general guidelines for dealing with software life cycle approaches that are unique, but which still fit into QSM's software measurement approach when some basic rules are applied for categorizing the life cycle phases.  Note that QSM consultants are available throughout the Basic Measures process to assist in the data collection and validation process.

### Throw-away Prototypes

In environments where prototypes are built to stabilize requirements and are subsequently discarded, include the time and effort spent building and verifying the prototypes in Phase 2.  Do not count the discarded software in the delivered code count.

### Rapid-application Prototypes

In prototype or rapid application environments where the prototype will be used in the delivered architecture, include all of the time and effort for each of the "prototype cycles" performed (design, code, integration, and user approval) as well as the time and effort to integrate and stabilize the final product in Phase 3.  If possible, determine the time and effort for Phase 2 by taking a percentage of the total time and effort spent defining software requirements.

### Enhancements, Modifications, and Large-scale Maintenance

For enhancements, modifications, and large-scale maintenance efforts that are beyond the scope of the parent project’s Phase 4, include the time and effort for analysis of potential modifications/changes in Phase 2.  Creation and modification of design and code plus integration should be included in Phase 3.  Be careful to break out the delivered code size in terms of new, modified, and unmodified so that the degree of re-use is accurately represented.

## Software Sizing

The way in which sizing units are counted is critical to reducing variation in an organization’s size-dependent metrics.  Organizations should define precisely the rules by which their sizing units will be counted or excluded.  QSM recommends the guidelines that have been established by the Software Engineering Institute for counting Logical Source Statements (LSS).  The LSS measure is used to count software instructions independent of the physical format in which they appear.  For example, if two source statements were to appear on one single line, this method would count two source statements.  If one instruction spanned two lines, the count would be one.

In order to define the precise rules by which software can be counted, it is necessary to describe some of the attributes used to categorize software.  There are three attributes in particular that must be considered.  They are:

- Type Attribute -- Classifies each source statement as either executable, data declaration, compiler directive, or comment.

- Origin Attribute -- Classifies software as either developed or non-developed.

- Usage Attribute -- Classifies software as either deliverable or non-deliverable.

### Type Attribute

| Type of Source Statement | Description | Include in Count |
| --- | --- | --- |
| Executable | Source statements which direct the actions of the target computer. | Yes |
| Data Declaration | Source statements which reserve or change memory at compilation time, are compile time directives to check data, define the structure of the data that will reserve or allocate or create memory at run time. | Yes |
| Compiler Directive | Source statements which define macros, are labels, direct the compiler to insert external source statements (for example, include statements), direct conditional compilation, or are not described by one of the other type of attributes. | Yes |
| Comment | Source statements that provide information to people reading the source code and are ignored by the compiler. | No |

### Origin Attribute

| Origin of Source Statement | Description | Include in Count |
| --- | --- | --- |
| Developed | Source statements created or modified for the specific project being measured. Created statements are those that did not previously exist and were created specifically for this project. Modified statements are those taken from another software product to which changes were made to make the software suitable for this application. | Yes |
| Non-Developed | Source statements that were not originally developed for this project. These include deleted source statements (those removed from a previously developed software product to make the remaining source statements form a product useful for this application) and reused source statements (those obtained for the project from an external source; e.g., from a previous version of this product, a reuse library, or acquired software which are left unmodified). | Included in Total Size; not included in Effective Size |

### Usage Attribute

| Usage of Source Statement | Description | Include in Count |
| --- | --- | --- |
| Deliverable | All software developed as part of the project and intended to be delivered to the customer. This includes all source statements incorporated in the final product, source statements delivered to the customer to support acceptance and certification of the final product (even if those source statements are not used by the customer), and all source statements that support the product in its operating environment; e.g., installation programs, diagnostics, and support utility software. | Yes |
| Non-Deliverable | All software developed as part of the project but not intended to be delivered to the customer. This category typically includes all source statements that were produced to support the development process; e.g., development tools, utilities, and test drivers. | No |

# Description of Data

## Basic Information

### Project Information

Project Name:  System name or project title.

Status:  Indication of the current state of the project; choose one of the following:
	Estimate - The collected data are estimated
	In Progress - The collected data contain partial actuals
	Completed - The collected data contain final actuals

Confidence:  Label that best describes the level of confidence in the accuracy and consistency of this project’s data; choose one of the following:
	Low - Low Confidence (error  10%)
	Medium - Medium Confidence (5%  error  10%)
	High - High Confidence (error  5%)

Predominant Application Type:  Label that best describes the application type most heavily represented in this system; choose one Major (Minor) pair from the following:  Microcode / Firmware (General Purpose CPU, IO Controller, Memory Mgmt Unit, Image Processor, Signal Processor, ASIC, Other), Realtime (Robotics, Sensors, Signal Processors, Firmware, Controllers, Embedded Systems, On-board Space, Cell Phone, Simulators, Test Rigs, Other), Avionic (Air Traffic Management, Navigation, Sensors, Displays, Flight Communications, Reference, Entertainment, Maintenance, Environment, Weapons, Countermeasures, Surveillance, Other), System Software (Operating System, Environments, Middle Ware, Tools (DBMS, etc.), Compilers, Network Mgmt, LAN/WAN OS, Game Software, Other), Command & Control (Mission Planning, Air Traffic Control, Fire Control, Other), Telecom / Message Switching (Switches, Modems, Network Mgmt, Routers, PBX Systems, Other), Scientific (Statistical, Decision Support, AI, Statistical Analysis, High Security/Encryption, Other), Process Control (Automated Plant Control, Industrial Automation, Other), Business (Billing, Sales, Human Resources, Payroll, Trading, Funds Transfer, Inventory Control, Facility Mgmt, Financial Mgmt, Materials Mgmt, Flow Control, Network Support, Order Entry, Database Mgmt, Accounting, Executive Mgmt, Customer Care, Reservations, Other)

Description:  Overview of the system under development.

### Sizing

New Source Statements:  Portion, measured in logical source statements, of the total system size that was developed for this application (designed, coded, integrated, and tested from scratch).

Modified Source Statements:  Portion, measured in logical source statements, of the total system size contained in pre-existing entities (modules, packages, etc.) that were modified (pre-existing software requiring changes).

Unmodified Source Statements:  Portion, measured in logical source statements, of the total system size contained in pre-existing entities (modules, packages, etc.) that were incorporated into this product unchanged (pre-existing software requiring no changes).

Total System Source Statements:  Total number of source statements contained in the delivered system.

Requirements:  Total number of requirements (new and pre-existing requiring changes) representing the work done by this project.

### Defects

System Integration to Delivery:  Total number of defects found between SIT and FOC in the deliverables produced during Phase 3 (Main Build).  SIT (System Integration Test) is a QSM-defined milestone that represents the point at which the first configuration item (e.g., module, package, compilation unit) is placed under change control and is ready to be integrated into the evolving system.  FOC (Full Operational Capability) is a QSM-defined milestone that represents full functionality with 95% reliability.

First Month after Delivery:  Total number of defects found during the first month following FOC in the deliverables produced during Phase 3 (Main Build).  FOC (Full Operational Capability) is a QSM-defined milestone that represents full functionality with 95% reliability.

### Time and Effort

For each of the four life cycle phases and the entire life cycle (where appropriate), provide the following information:

Start Date:  The date on which effort was first applied to any activities of the associated life cycle phase.  Note that phases may overlap or be separated by gaps.

End Date:  The date on which all activities of the associated life cycle phase were completed.  Note that phases may overlap or be separated by gaps.

Effort (PM):  Total person-months of labor to complete all activities of the associated life cycle phase.

Cost (1000 $):  Total cost, in thousands of U.S. dollars, to complete all activities of the associated life cycle phase.

Peak Staff:  Peak number of full time equivalent (FTE) people used to complete all activities of the associated life cycle phase.

Staffing Shape:  Label that best describes the shape of the staffing curve for the associated life cycle phase; choose one of the following:
	Unknown - Valid for any of the four life cycle phases.
	Front Load Weibull - Valid for any of the four life cycle phases.
	Normal - Valid for any of the four life cycle phases.
	Rear Load Weibull - Valid for any of the four life cycle phases.
	Custom - Valid for any of the four life cycle phases.
	Level Load - Valid for Phases 1, 2, and 3 only.
	Front Load Rayleigh - Valid for Phases 1, 2, and 3 only.
	Medium Front Load Rayleigh - Valid for Phases 1, 2, and 3 only.
	Medium Rear Load Rayleigh - Valid for Phases 1, 2, and 3 only.
	Rear Load Rayleigh - Valid for Phases 1, 2, and 3 only.
	Default Rayleigh - Valid for Phases 1, 2, and 3 only.
	Stair Step - Valid for Phase 4 only.
	Straight Line - Valid for Phase 4 only.
	Exponential - Valid for Phase 4 only.
	Rayleigh - Valid for Phase 4 only.

## Staffing Detail

### Staffing – nth 12 Months

For each month of the project, for each of the four life cycle phases including total; provide the average number of full time equivalent (FTE) people working on the corresponding phase activities during the corresponding month.  Label each month column with its corresponding month and year (mm/dd).

## Application

### Project Summary

Organization:  The name of the company or organization entity that was responsible for the project.

Division:  The name of the organization’s particular business unit that was responsible for the project.

Country:  The name of the country in which the project was done.

Design Complexity:  Label that best describes the complexity of the developed system; choose one of the following:  Low, Moderate, High

Development Classification:  Label that best describes the type of development effort undertaken by the project; choose one of the following:  New Development, Major Enhancement (25-75% new), Minor Enhancement (5-25% new), Conversion (<5% new), Maintenance

Industry Sector:  Label that best describes the market addressed by product under development; choose one Major (Minor) pair from the following:  Academic (General), Aerospace (General Aviation, Commercial, Military), Construction (General), Distribution (General), Military (General), Electronics (General), Engineering (General), Financial (General, Banking, Insurance), Government (General, National, Local, State, County), Leisure (General, Entertainment, Hotel), Manufacturing (General, Airplane, Automobile, Brewery, Chemical, Computer, Comp Peripherals, Image Processing, Medical, Pharmaceutical, Software, Telecom Equipment), Health (General), Mining (General, Metals, Gem, Coal), Oil (General), Retail (General, Food, Clothing), Service (General, Consulting), Transportation (General, Air, Bus, Rail/Metro, Sea, Trucking), System Integrators (General), Utilities (General, Gas, Electric, Telecom, Water), Other (General)

### Application Type

For each of the listed application types, provide the percentage of the total system size dedicated to the associated application type.

### Predominant Development Machine

Type:  Label that best describes the general type of the host development machine; choose one of the following:  Microcomputer/Standalone PC, Workstation, Client/Server, Minicomputer, Mainframe

Specific:  The specific name and version of the host machine.

### Predominant Operating System

Type:  Label that best describes the general type of the host operating system; choose one of the following:  AIX, AS/400, DOS (non Window), HPUX, ICL, MAC, MVS, Open VMS, OS/2, OSF/1, PICK, POSIX, Solaris, Ultrix, VM, VM/CMS, VME, VMS, VMS (DEC) VSE, Windows, Windows NT, X-Windows, Xenix, Other

Specific:  The specific name and version of the host operating system.

## Sizing

### Function Unit Totals

For each different sizing unit used, provide the following information:

Function Unit:  The name of a sizing unit used to size the system; choose one of the following:  Source Statements, Function Points, Feature Points, Subsystems, Programs, Modules, Objects, Entities, Processes, CSU, CSCI, CSC, Mark II Function Pts, Method II Function Pts, Dialogs, Actions, Screens, Reports, Windows, Logical Input Stmts, BANGS, USE Cases, Methods, Classes, Bytes

Total:  The total size of the system in the associated sizing units.

Gear Factor:  The factor that, when multiplied by the Total above, yields the total system size in logical source statements.

Counting:  The method used for counting the associated sizing unit; choose one of the following:  Manual, Estimated, Sampled, Code Counter

New:  The portion of this sizing unit’s total that was designed, coded, integrated, and tested from scratch.

Mod:  The portion of this sizing unit’s total contained in pre-existing entities (modules, packages, etc.) that were modified (pre-existing software requiring changes).

Unmod:  The portion of this sizing unit’s total contained in pre-existing entities (modules, packages, etc.) that were incorporated into this product unchanged (pre-existing software requiring no changes).

Note that New + Mod + Unmod must equal Total for each row.

### Language Breakdown for Logical Source Statements (LSS)

For each different language used, provide the following information:

Language:  The name of a language used to code the system.

Type:  The language type that best describes the level of the associated language; choose one of the following:  High Order/3rd GL, Low Level, 4th Generation, Microcode, Object-Oriented, DBMS, JCL, Special Language, GUI, Forms/Table-based, Frames, Other

Total:  The portion (in LSS) of the total system size accounted for by this language.

Gear Fctr:  The factor that, when multiplied by the total number of associated language units (statements, sentences, graphic objects, etc.) yields an equivalent number of LSS written in a third-generation programming language (e.g., Ada, C, or Pascal).

New:  The portion (in LSS) of the associated language code that was designed, coded, integrated, and tested from scratch.

Mod:  The portion (in LSS) of the associated language code contained in pre-existing entities (modules, packages, etc.) that were modified (pre-existing software requiring changes).

Unmod:  The portion (in LSS) of the associated language code contained in pre-existing entities (modules, packages, etc.) that were incorporated into this product unchanged (pre-existing software requiring no changes).

Note that New + Mod + Unmod must equal Total for each row.

## Accounting

### Effort

Effort Units:  The name of the effort unit used for all labor-related data; choose one of the following:  Manyear, Manmonth, Manweek, Manday, Manhour, Personyear, Personmonth, Personweek, Personday, Personhour, Staffyear, Staffmonth, Staffweek, Staffday, Staffhour

Average # of person hours per person month:  The average number of hours a typical Full Time Equivalent (FTE) employee works in a normal month allowing for vacation, holidays, and paid personal time off.

### Labor Rate

Labor Rate:  The burdened cost of an average employee in the selected Monetary Units per the selected Labor Rate Unit.

Monetary Unit:  The name of the monetary unit used for all cost-related data; choose one of the following:  $, C$, YEN, R, A$, RA, BP, DG, BF, FF, L, DM, SF, LF, PE, SC, NKR, SKR, MA, ECU, OTH

Labor Rate Units:  The name of the effort unit associated with the given Labor Rate; choose one of the following:  Manyear, Manmonth, Manweek, Manday, Manhour, Personyear, Personmonth, Personweek, Personday, Personhour, Staffyear, Staffmonth, Staffweek, Staffday, Staffhour

Conversion Factor (to $US):  The factor that, when multiplied by an amount expressed in the selected Monetary Units, yields an equivalent amount in United States dollars.

## Custom Fields

Complete these fields according to the provided Organization-Specific Instructions.  If no such instructions are provided, leave these fields blank.

## Environment

Evaluate each aspect of the project’s development environment according to the scale shown in the Evaluation Values box.

### Summary Evaluation

Tooling and Methods:  The aggregate rating for the project’s use of tools and methods; choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Technical Difficulty:  The aggregate rating for the technical difficulty of the product; choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Personnel Profile:  The aggregate rating for the knowledge and experience present in the development team; choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

### Tooling and Methods Detailed Evaluation

#### Development System

Hardware Familiarity:  How familiar was the team with the development hardware?

- Low end of scale, 0-2 range.  No experience or minimal experience with this development hardware.

- QSM Database average, 5 on the scale.  Team has previous experience of 1-2 projects.

- High end of scale, 9-10 range.  Team has previous experience on 5 or more projects.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Availability:  How available was the development system?

- Low end of the scale, 0-2 range.  Design, code, integration, and test facilities are available less than 50% of the time when they are required.

- QSM Database average, 5 on the scale.  Design, code, integration, and test facilities are available 72% of the time when they are required.

- High end of scale, 9-10 range.  Design, code, integration, and test facilities are available more than 97% of the time when they are required.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Database Management System (DBMS)

Role:  How extensive was the role of the database management system?

- Low end of scale, 0-2 range.  No data or minimal data was required to be stored, retrieved, and manipulated.  No commercial DBMS was used.  Data storage and retrieval routines were simple and straightforward.

- QSM Database average, 5 on the scale.  A commercial database management product was used for data storage and retrieval.  The volume of data and transactions were well within the capacity and throughput limit of the DBMS.

- High end of scale, 9-10 range.  A commercial database management system product was used for storage and retrieval or a simple DBMS was created.  The volume of data and transactions is enormous and was a key component of the successful development of this product.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Tools Capability:  What was the DBMS tools capability?

- Low end of scale, 0-2 range.  There was a good DBMS engine but no tools were available within the environment to define, build, manipulate, and extract information from the engine.

- QSM Database average, 5 on the scale.  There was a good DBMS engine and some tools were available within the environment to define, build, manipulate, and extract information from the engine.

- High end of scale, 9-10 range.  There was a good DBMS engine and a great set of tools was available within the environment to define, build, manipulate, and extract information from the engine.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Screen Writer

Screen Intensity (volume):  How screen intensive is the system?

- Low end of scale, 0-2 range.  Less than 10% of the total functionality in the system is screens.

- QSM Database average, 5 on the scale.  45% to 60% of the total functionality in the system is screens.

- High end of scale, 9-10 range.  Greater than 85% of the total functionality in the system is screens.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Capability:  What was the screen writer capability?

- Low end of scale, 0-2 range.  No or very few tools existed to design and build screens.

- QSM Database average, 5 on the scale.  Some tools existed to design and build screens.

- High end of scale, 9-10 range.  Excellent GUI building tools existed to build screens.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Report Writer

Report Intensity (volume):  How report intensive is the system?

- Low end of scale, 0-2 range.  Less than 10% of the total functionality in the system is reports.

- QSM Database average, 5 on the scale.  45% to 60% of the total functionality in the system is reports.

- High end of scale, 9-10 range.  Greater than 85% of the total functionality in the system is reports.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Capability:  What was your screen writer capability?

- Low end of scale, 0-2 range.  No tools existed to design and build reports.

- QSM Database average, 5 on the scale.  Some tools existed to design and build reports.

- High end of scale, 9-10 range.  Excellent GUI building tools existed to build reports.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### File Handling

File Intensity (volume):  How intensive is the file handling in this system?

- Low end of scale, 0-2 range.  Very few physical files exist in the design of the system.  Access to the files is limited.

- QSM Database average, 5 on the scale.  A moderate number of files exist in the design of the system.  Access to those files is required on a regular basis.

- High end of scale, 9-10 range.  Large number of files exist in the design of the system.  Access to those files is required on a frequent basis and is quite complicated.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Capability:  What was the capability of the file handling tools?

- Low end of scale, 0-2 range.  No or very few tools existed to open, close, and manipulate files.

- QSM Database average, 5 on the scale.  Some tools existed to open, close, and manipulate files.

- High end of scale, 9-10 range.  Excellent GUI building tools existed to open, close, and manipulate files.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Tool Capability / Use

Diagramming:  How well did the team use diagramming tools?

- Low end of scale, 0-2 range.  No requirements, design, or performance modeling is used.

- QSM Database average, 5 on the scale.  Modeling is used to some degree, skills training is required.

- High end of scale, 9-10 range.  Excellent integrated modeling tools are used and people are highly proficient in their use.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Testing:  How well did the team use testing tools?

- Low end of scale, 0-2 range.  No formal tools or process was used.

- QSM Database average, 5 on the scale.  Test plans and scripts were created for unit, integration, and system level test.  Automated regression testing facilities were in place.

- High end of scale, 9-10 range.  Full range of test plans and procedures were in place.  A dedicated test facility that was a mirror image of the customer’s production facility was in use.  Regression testing, capture and play-back, and debugging tools were used extensively.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Programming:  How well did the team use programming tools?

- Low end of scale, 0-2 range.  No commercial programming tools were available.  No internal programming tools were available.  Programmers used a compiler with very limited aids.  All tools had to be created by the programmers.

- QSM Database average, 5 on the scale.  The language compiler had reasonable capabilities including basic editing, trace, multiple compile switches, and debugging features.  Performance of the compiler was adequate.

- High end of scale, 9-10 range.  The language compiler was full-functioned with superior editing, trace, multiple compile switches, and debugging features.  The compiler was very fast and efficient.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Configuration Management:  How well did the team use configuration management tools?

- Low end of scale, 0-2 range.  No formal code library system was in use.  Access and change control was ad hoc and chaotic.

- QSM Database average, 5 on the scale.  A formal library existed.  Control of changes to the code was supervised in a semi-formal fashion.

- High end of scale, 9-10 range.  A highly automated and formal process was used and adhered to whereby strict control over code changes was managed.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Project Management:  How well did the team use project management tools?

- Low end of scale, 0-2 range.  No formal estimation, macro planning or detailed planning took place.  No project tracking process was in place.

- QSM Database average, 5 on the scale.  Estimation was performed using expert judgment.  Detailed plans were created at the beginning of the project but were not updated consistently as things changed during the project.  Effort and milestone tracking was performed.

- High end of scale, 9-10 range.  Estimation was performed by models that were calibrated by the development organization’s historic data.  The models generated high-level plans, alternatives, and risk evaluations.  High-level plans fed the detailed planning process.  Effort, milestones, code production, and defects were tracked and used for adaptive forecasts.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Documentation:  How well did the team use documentation tools?

- Low end of scale, 0-2 range.  Documentation was created in an ad hoc manner.  No specialized tools were used and no formal templates were created.

- QSM Database average, 5 on the scale.  Templates existed and were used frequently.  Tool sets that produced documents were loosely integrated which required some rekeying and expensive formatting changes.

- High end of scale, 9-10 range.  Documentation and development tools were used to a high degree.  Integration was smooth between these tools so no rekeying or formatting was required.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Quality Assurance:  How well did the team use quality assurance tools?

- Low end of scale, 0-2 range.  No formal quality assurance program was used.  If it was used, it was not effective because the project people only paid lip service to the inspection techniques that were employed during requirements, design, coding, and test.

- QSM Database average, 5 on the scale.  A formal method was in place.  It was supported by some level of automation and was used.

- High end of scale, 9-10 range.  There was a very formal method and the project bought in to the process because of benefits that had been demonstrated on past efforts.  There was a high degree of automation and adherence to the methods.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Database Conversion:  How good were the database conversion utilities?

- Low end of scale, 0-2 range.  Few tools existed.  Most routines had to be created by the programmers.

- QSM Database average, 5 on the scale.  Conversion utilities were in existence but had to be modified by 15% to 20% to meet the requirements of the new system.

- High end of scale, 9-10 range.  Conversion utilities were available and required no changes.

Choose one of the following:  U(Unknown/na), 0-No Tools, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Integration:  How well were the tools integrated?

- Low end of scale, 0-2 range.  Tools were totally independent.

- QSM Database average, 5 on the scale.  Tools had a moderate degree of integration but was far from ideal.

- High end of scale, 9-10 range.  Had a tightly integrated CASE environment.  Products from one stage of development were seamlessly transformed and fed into the next stage of development.

Choose one of the following:  U(Unknown/na), 0-No Integration, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Development Standards

Robustness:  How robust were the development standards?

- Low end of scale, 0-2 range.  The standards in place were a framework but were incapable of working for 75% of the projects that were typical of the work being done.

- QSM Database average, 5 on the scale.  The standards in place were a good framework and could handle 75% of the typical projects.

- High end of scale, 9-10 range.  The standards in place were ideal and were capable of handling 98% of all projects and situations that typically occur.

Choose one of the following:  U(Unknown/na), 0-No Standard, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Adherence:  How well did the team adhere to the development standards?

- Low end of scale, 0-2 range.  The standards sat on a shelf untouched and not followed.

- QSM Database average, 5 on the scale.  70% of the team used the standard; however, whenever they felt time pressure, they took shortcuts.

- High end of scale, 9-10 range.  The standards were always used by the entire project and no variations from the standards were accepted.

Choose one of the following:  U(Unknown/na), 0-No Standard, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Experience:  What was the team’s level of experience with the development standards?

- Low end of scale, 0-2 range.  One small pilot project.

- QSM Database average, 5 on the scale.  Two to four typical projects.

- High end of scale, 9-10 range.  Greater than four typical projects.

Choose one of the following:  U(Unknown/na), 0-No Standard, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Adaptability:  How well could the development standards be tailored to systems of different types and sizes?

- Low end of scale, 0-2 range.  Extremely inflexible; for one type of scenario only.

- QSM Database average, 5 on the scale.  Could accommodate 70% of all typical cases.

- High end of scale, 9-10 range.  Could handle 98% of all typical cases.

Choose one of the following:  U(Unknown/na), 0-No Standard, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

### Technical Difficulty Detailed Evaluation

#### Constraints

Memory Intensity:  How memory intensive is this system?

- Low end of scale, 0-2 range.  The available memory is abundant.  No special considerations were required in designing and constructing this system with respect to memory.

- QSM Database average, 5 on the scale.  This application used up to 65% of the available memory on the hardware on which it is deployed.

- High end of scale, 9-10 range.  This application used all of the available memory.  Designers and programmers had to constantly optimize their routines to fit within the memory restriction of the target hardware system.

Choose one of the following:  U(Unknown/na), 0-No Constraint, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Data Intensity:  How data intensive is this system?

- Low end of scale, 0-2 range.  The volume of data and time-constrained processing this system is required to handle is well within the limits of its computational and throughput capacity.

- QSM Database average, 5 on the scale.  The volume of data and time-constrained processing this system is required to handle marginally tests the limits of its computational and throughput capacity.

- High end of scale, 9-10 range.  The volume of data and time-constrained processing this system is required to handle stresses the limits of its computational and throughput capacity.

Choose one of the following:  U(Unknown/na), 0-No Constraint, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Data Manipulation:  How complex is data manipulation in this system?

- Low end of scale, 0-2 range.  Data rarely requires change from its original state.  If a transformation is required, it is simple and the amount of time required to perform the transform is easily performed with the computing resources that are available.

- QSM Database average, 5 on the scale.  Up to 20% of the data that is received has to undergo some transformation.  The transformation is relatively straightforward.

- High end of scale, 9-10 range.  Data is being received from remote sensors.  The data must be changed using complicated transformation algorithms in milliseconds and is passed on to other areas for real time processing.

Choose one of the following:  U(Unknown/na), 0-No Constraint, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### New Algorithms

Relative Volume:  What was the volume of new algorithms in this system?

- Low end of scale, 0-2 range.  Less than 10% of the algorithms were new.

- QSM Database average, 5 on the scale.  No more than 40% of the algorithms were new.

- High end of scale, 9-10 range.  Greater than 90% of the algorithms were new.

Choose one of the following:  U(Unknown/na), 0-No Constraint, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Relative Complexity:  What was the complexity of developing the new algorithms?

- Low end of scale, 0-2 range.  The algorithms were simple (arithmetic expression) mathematics.

- QSM Database average, 5 on the scale.  The algorithms were a mix of simple (arithmetic expression) mathematics and complex (non-linear, function-oriented) mathematics with simple procedures (decision, iteration).

- High end of scale, 9-10 range.  The algorithms contained extremely complex mathematics coupled with complex procedures (recursion).

Choose one of the following:  U(Unknown/na), 0-No Constraint, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### New Logic

Relative Volume:  What was the volume of new logic in this system?

- Low end of scale, 0-2 range.  Less than 25% of the logic was new.

- QSM Database average, 5 on the scale.  No more than 75% of the logic was new.

- High end of scale, 9-10 range.  Greater than 90% of the logic was new.

Choose one of the following:  U(Unknown/na), 0-No Constraint, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Relative Complexity:  What was the complexity of developing the new logic?

- Low end of scale, 0-2 range.  The logic is simple (combinatorial).

- QSM Database average, 5 on the scale.  A mix of simple (combinatorial) and complex (sequential) logic.

- High end of scale, 9-10 range.  Extremely complex logic coupled with many interdependencies.

Choose one of the following:  U(Unknown/na), 0-No Constraint, 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Complexity

Requirements Volatility:  What was the volume of requirements changes?

- Low end of scale, 0-2 range.  The requirements were well known and did not change more than 5%.

- QSM Database average, 5 on the scale.  Up to 50% of the requirements were not sufficiently defined at the beginning of the project and up to 20% changed during development.

- High end of scale, 9-10 range.  The requirements were very fuzzy and ill defined at the beginning of the project and over 50% changed during development.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Customer Interface:  How complex was the customer interface?

- Low end of scale, 0-2 range.  The developer and customer have a good relationship.  They work together as partners and are open and considerate of each other.  They are creative at solving problems.

- QSM Database average, 5 on the scale.  Some friction exists but the developer and customer generally work together and have a reasonable relationship.

- High end of scale, 9-10 range.  Enormous friction exists between customer and developer.  A lot of energy is expended fighting battles which could be going into systems building.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

External System Interface:  How complex is the external system interface?

- Low end of scale, 0-2 range.  This is a standalone system which has no interfaces to other products or systems.

- QSM Database average, 5 on the scale.  This system has several automated interfaces to other systems.  The interfaces are well defined.

- High end of scale, 9-10 range.  This system has automated interfaces to many systems.  The interfaces have not been defined and are extremely complex.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Code Integration and Testing:  How complex was code integration and testing?

- Low end of scale, 0-2 range.  The integration of the various pieces of the system was relatively easy.

- QSM Database average, 5 on the scale.  The integration and testing of the various pieces of the system was about average for this application type.

- High end of scale, 9-10 range.  The integration and testing of the various pieces of the system will be very difficult and complex.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Documentation Intensity:  How intensive were the documentation requirements?

- Low end of scale, 0-2 range.  This product required little formal documentation.  It is for use internal to the company.

- QSM Database average, 5 on the scale.  This product required a complete set of user documentation but the design documents did not have to be formally delivered to the customer.

- High end of scale, 9-10 range.  The development standard required full documentation for requirements, design, test, maintenance, user manuals, etc.  There was a very heavy overhead associated with the creation of documentation.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Platform Stability

Target System:  How stable was the target system?

- Low end of scale, 0-2 range.  The target system was very unreliable.  It was developed concurrently with the product software.

- QSM Database average, 5 on the scale.  The project started with a complete target system that had at least nine months of general availability.  It was reasonably reliable but periodically exhibited problems.

- High end of scale, 9-10 range.  The project started with a complete target system that was mature and very reliable.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Host (Development) System:  How stable was the host (development) system?

- Low end of scale, 0-2 range.  The development system (host hardware, operating system, compilers, linkers, debuggers, simulators, network systems, etc.) was very unreliable.  It was developed concurrently with the product software.

- QSM Database average, 5 on the scale.  The project started with a complete development system that had at least nine months of general availability.  It was reasonably reliable but periodically exhibited problems.

- High end of scale, 9-10 range.  The project started with a complete development system that was mature and very reliable.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

### Personnel Profile Detailed Evaluation

#### Management / Leadership

Effectiveness:  How good was the management and leadership on this project?

- Low end of scale, 0-2 range.  Very little leadership, guidance, and employee empowerment took place.

- QSM Database average, 5 on the scale.  Competent management was in place on the project.

- High end of scale, 9-10 range.  Management created an exceptional environment where people love their work and seek out ways to improve all aspects of their work processes.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Environment

Training Availability:  What was the availability of training?

- Low end of scale, 0-2 range.  No money was ever budgeted for training.  It was very difficult to attain formal training.

- QSM Database average, 5 on the scale.  Some money was budgeted for training.  The company mandated that employees attend a minimum of five days of professional training every year.

- High end of scale, 9-10 range.  Professional education is deemed very important and was made available whenever special circumstances dictated.  A regular program was in place where employees got a minimum of two weeks per year.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Staff Turnover:  What was the level of staff turnover?

- Low end of scale, 0-2 range.  Staff turnover on the project team did not exceed 5%.

- QSM Database average, 5 on the scale.  Staff turnover on the project team did not exceed 15%.

- High end of scale, 9-10 range.  Staff turnover on the project team was greater than 50%.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Development Team

Skill Level:  What was the availability of skilled manpower?

- Low end of scale, 0-2 range.  80% of the team were new hires with little experience in building software products.

- QSM Database average, 5 on the scale.  65% of the team were experienced system builders; 35% had little experience.

- High end of scale, 9-10 range.  90% of the team were experienced people and only 10% had little experience.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Functional Knowledge:  What was the level of functional knowledge?

- Low end of scale, 0-2 range.  Team members had very little understanding of the type of problem that was to be solved by this application.

- QSM Database average, 5 on the scale.  Team members had a good grasp of the problem the application was attempting to solve.

- High end of scale, 9-10 range.  Team members were expert in the application domain of the software.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Experience with Application:  How experienced was the development team with this application type?

- Low end of scale, 0-2 range.  80% of the team members had never set eyes on this application.

- QSM Database average, 5 on the scale.  60% of the team members had worked on this application in the past.

- High end of scale, 9-10 range.  Greater than 80% of the team members had worked on this application in the past.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Motivation:  How motivated was the development team?

- Low end of scale, 0-2 range.  Team members displayed little initiative?

- QSM Database average, 5 on the scale.  Team members were generally positive and hard working.

- High end of scale, 9-10 range.  Team members were full of energy, were self-motivated, and extremely positive.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Cohesiveness:  How cohesive was the development team?

- Low end of scale, 0-2 range.  Personality types were in conflict which could not be resolved.  Animosities existed which constantly caused problems.

- QSM Database average, 5 on the scale.  People got along well enough.  Occasionally problems emerged but they were resolved quickly.

- High end of scale, 9-10 range.  Tightly knit team; everyone was on the same wavelength.  Relations were excellent.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Human Communication:  What was the level of human communication complexity?

- Low end of scale, 0-2 range.  Procedures and practices were routinely followed.  Communication problems were essentially eliminated through this practice.

- QSM Database average, 5 on the scale.  Procedures had been established and were generally followed.

- High end of scale, 9-10 range.  Communication channels frequently broke down, often leading to major problems.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

### Reused, Unmodified Software Detailed Evaluation

#### Size

Relative Magnitude:  What was the relative % of reused software?

- Low end of scale, 0-2 range.  0% to 20% of the system represents reused functionality.

- Middle of the scale, 4-6 range.  50% of the system represents reused functionality.

- High end of scale, 8-10 range.  80% to 99% of system represents reused functionality.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

#### Complexity and Difficulty

Integration Complexity:  What was the level of complexity of integrating products with new code?

- Low end of scale, 0-2 range.  There was minimal complexity integrating the reused software products with the new code.  There were not many interfaces necessary.  The interfaces needed were well understood, simple, well isolated, and straightforward.

- Middle of the scale, 4-6 range.  The job of integrating the existing software was moderately difficult.  Either many simple interfaces or a limited number of complex interfaces were required.

- High end of scale, 9-10 range.  The job of integrating the existing software was extremely complex.  Often this software was very old, there were many interfaces, and a significant portion of the existing software needed to be modified in many scattered places.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Experience with Reused Functionality:  What was the level of experience using the specific products?

- Low end of scale, 0-2 range.  Team members had minimal or no development experience using the commercial packages and/or existing code.

- Middle of the scale, 4-6 range.  Team members had previous development experience using the commercial packages and/or existing code on one project.

- High end of scale, 8-10 range.  Team members had previous development experience using the commercial packages and/or existing code on two or more projects or has had intensive experience on one project.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Functional Interfaces Present:  What was the relative number of functional interfaces present?

- Low end of scale, 0-2 range.  There were fewer than 20 functional interfaces.

- Middle of the scale, 4-6 range.  There were 100 to 150 functional interfaces.

- High end of scale, 8-10 range.  There were greater than 500 functional interfaces.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Functional Interfaces Used:  What was the relative percent of functional interfaces that were used?

- Low end of scale, 0-2 range.  1% to 20% of the functional interfaces present were used.

- Middle of the scale, 4-6 range.  40% to 60% of the functional interfaces present were used.

- High end of scale, 8-10 range.  80% to 100% of the functional interfaces were used.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Functional Interface Complexity:  What was the complexity of using the functional interfaces?

- Low end of scale, 0-2 range.  The functional interfaces were simple, easy to learn and use.

- Middle of the scale, 4-6 range.  There was a mix of simple and complex functional interfaces.

- High end of scale, 8-10 range.  The functional interfaces were extremely complex, difficult to learn and use.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Selection Time:  What was the research time required to select products?

- Low end of scale, 0-2 range.  0% to 5% of the total schedule was dedicated to researching and selecting reusable software products.

- Middle of the scale, 4-6 range.  8% to 14% of the total project schedule was dedicated to researching and selecting reusable software products.

- High end of scale, 8-10 range.  18% to 20% or greater of the total project schedule was dedicated to researching and selecting reusable software products.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Impact Analysis Effort:  What was the analysis effort required to assess impact to existing code?

- Low end of scale, 0-2 range.  0% to 5% of the total project schedule was dedicated to assessing the impact to existing code.

- Middle of the scale, 4-6 range.  8% to 14% of the total project schedule was dedicated to assessing the impact to existing code.

- High end of scale, 8-10 range.  18% to 20% or greater of the total project schedule was dedicated to assessing the impact to existing code.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Documentation Usefulness:  What was the clarity and usefulness of documentation, if it was required?

- Low end of scale, 0-2 range.  Little formal documentation was available.  What was available was of limited use.

- Middle of the scale, 4-6 range.  There was documentation available on using and interfacing with the reused software, but it was only moderately effective.

- High end of scale, 8-10 range.  There was extensive documentation on using and interfacing with the reused software and it was highly effective.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Customer Support Effectiveness:  What was the effectiveness of external customer support, if required?

- Low end of scale, 0-2 range.  It was very difficult to communicate with the developers and supporters of the reused software.  When available, the support was of questionable benefit.

- Middle of the scale, 4-6 range.  Customer support personnel were moderately helpful when problems or questions about using the software came up.  There was usually a 2 to 3 day turnaround in getting responses.

- High end of scale, 8-10 range.  Customer support personnel were extremely knowledgeable and helpful when problems or questions about the reused software occurred.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Additional Documentation Required:  What was the level of additional user documentation required for reused products?

- Low end of scale, 0-2 range.  Less than 20% of the total documentation effort was dedicated to documenting the reused software.

- Middle of the scale, 4-6 range.  25% to 50% of the total documentation effort was dedicated to documenting the reused software.

- High end of scale, 8-10 range.  More than 75% of the total documentation effort was dedicated to documenting the reused software.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

Additional Regression Testing Required:  What was the level of additional regression testing required for reused products?

- Low end of scale, 0-2 range.  0% to 5% of the total testing was devoted to the reused portion of the software.

- Middle of the scale, 4-6 range.  40% to 60% of the total testing was devoted to the reused portion of the software.

- High end of scale, 8-10 range.  More than 75% of the total testing was devoted to the reused portion of the software.

Choose one of the following:  U(Unknown/na), 0(None), 1(Low), 2, 3, 4, 5(Average), 6, 7, 8, 9, T(High)

## Quality

### Development Runtime Environment

#### Exposure

days / week:  The number of days per week that the development runtime environment was up and running.

hours / day:  The number of hours per day that the development runtime environment was up and running.

minutes / hour:  The number of minutes per hour that the development runtime environment was up and running.

seconds / minute:  The number of seconds per minute that the development runtime environment was up and running.

#### Defects from System Integration to Delivery

Total Defects:  The total number of defects found between SIT and FOC in the deliverables produced during Phase 3 (Main Build).  SIT (System Integration Test) is a QSM-defined milestone that represents the point at which a configuration item (e.g., package, compilation unit, etc.) is placed under change control and is ready to be integrated into the evolving system.  FOC (Full Operational Capability) is a QSM-defined milestone that represents full functionality with 95% reliability.

Defects By Severity Class:  The name of a defect severity class used to categorize the set of total defects; the following are the preferred QSM defect severity classes:
	Critical - Renders product unusable.  Triggers an immediate re-release.
	Serious - Degraded operation; need workaround.  Triggers an unscheduled release.
	Moderate - Degraded operation; need workaround.  Must fix for next scheduled release.
	Tolerable - Near-normal operation.  Must fix for future scheduled release.
	Cosmetic - Near-normal operation.  Should fix for future scheduled release.
For each different defect severity class used by the project, provide the total number of defects found between SIT and FOC produced during Phase 3 (Main Build).  SIT (System Integration Test) is a QSM-defined milestone that represents the point at which a configuration item (e.g., package, compilation unit, etc.) is placed under change control and is ready to be integrated into the evolving system.  FOC (Full Operational Capability) is a QSM-defined milestone that represents full functionality with 95% reliability.  Note that the sum of all the Severity Class Defects should equal the Total Defects.

% of Total By Severity Class:  The percentage of the total number of defects represented by the associated defect severity class (Severity Class Defects / Total Defects * 100).

### Operational Runtime Environment

#### Exposure

days / week:  The number of days per week that the operational runtime environment was up and running.

hours / day:  The number of hours per day that the operational runtime environment was up and running.

minutes / hour:  The number of minutes per hour that the operational runtime environment was up and running.

seconds / minute:  The number of seconds per minute that the operational runtime environment was up and running.

#### Reliability at Delivery

MTTD 1st Month after Delivery:  The average time in days between discovery of new software defects during the first month of Phase 4 (Maintenance).

#### Defects After Delivery

First month:  The total number of defects found during the first month of Phase 4 (Maintenance).

First 3 months:  The total number of defects found during the first 3 months of Phase 4 (Maintenance).

First 6 months:  The total number of defects found during the first 6 months of Phase 4 (Maintenance).

First 9 months:  The total number of defects found during the first 9 months of Phase 4 (Maintenance).

First 12 months:  The total number of defects found during the first 12 months of Phase 4 (Maintenance).

First 18 months:  The total number of defects found during the first 18 months of Phase 4 (Maintenance).

## Defect Discovery Detail

### Defects – nth 12 Months

For each month of the project, for each of the five defect severity classes including total; provide the number of defects discovered of the corresponding severity class during the corresponding month.  Label each month column with its corresponding month and year (mm/dd).

## Review

### Overruns / Slippages (by planned value)

For each of the four life cycle phases and for the entire life cycle, provide the following information:

Time (months):  Baseline plan time in calendar months.

Effort (PM):  Baseline plan labor in person-months.

Cost (1000 $):  Baseline plan cost in thousands of U.S. dollars.

Peak Staff:  Baseline plan peak staff in number of FTE people.

### Growth / Reduction (by planned value)

Total System Size (Source Statements): Baseline plan total system size in logical source statements.

Requirements:  Baseline plan number of requirements.

### System Benefit/Effectiveness

Effectiveness Rating:

Choose one of the following: 0(No benefit), 1, 2 (Little benefit), 3, 4, 5(Average), 6, 7, 8(Beneficial), 9, 10(Most beneficial)

### Significant Factors

Describe any factors that had a positive or a negative impact on the project.  Provide the following for each listed factor:

Factor:  Descriptive short name of the factor.

Description:  A more detailed description of the factor.  This field is optional.

Impact:

Choose one of the following: 0(Very negative), 1, 2 (Negative), 3, 4, 5(No impact), 6, 7, 8(Positive), 9, 10(Very positive)

# Data Collection Forms

The following pages contain camera-ready copies of the actual forms on which the collected project data is to be recorded.  Please provide as much information as is reasonably possible.  It is especially important to complete all the fields on the BASIC INFORMATION sheet.  Try to use automated tools and historical records where possible to reduce the variability.  If a “guess” is the only way to provide necessary data then please provide the range of uncertainty around the guess (i.e., high, low, and most likely values).