## Slide 1: Transition to Metric Driven Management
QSM User Group
September 2006

## Slide 2: Duane Randall Sr. Project Manager Product Development Misys Hospital Systems

## Slide 3
Misys PLC
  FY2006 Revenue $1.8 billion
  U.K. based; 5th largest “pure” software company in the world
  Offices in 120 countries 5000+ employees
Healthcare Division
  HQ in Raleigh; Offices throughout U.S.
  Bangalore based development shop
Our Company

## Slide 4
Built through acquisition
Multiple technologies; development process models, cultures, etc.
Multiple Locations
Growth focused in Bangalore
ISO certified; FDA regulated products
Development Shop Environment

## Slide 5
“Quality
will transform our industry;
We will lead”
Business Drivers

## Slide 6
Lots of data; no actionable information
No measurement of output
  We knew how productive we were at creating bugs
No consistent measurements
Management by intuition
Business peers unhappy with productivity and quality
We can only provide vague assurances
  “We are as good as anyone else”
  Cold comfort at best
Where we started - September 2003

## Slide 7
An objective measurement model
Spanned the life cycle from business case estimation through delivery
Provided comparisons to others in the industry
Consistent methodology across
  Application types
  Technology
SLIM
Key to Transition

## Slide 8
Standard across the Healthcare division
Banking division interested in adoption
CMMI implementation in process
  SLIM key to measuring success
Where we are going!

## Slide 9
Scorecard for broad distribution across the business
  Board, executives, management team
  Overview
  Details; SLIM graphs
Performance Reporting

## Slide 10
Benchmark for broad distribution across the business
  Shows overall performance
  Trends release over release by product
  Basis of measuring MBO success
    Productivity
    Quality
Performance Reporting

## Slide 11
SLIM Quarterly Report
  First pass: Compare projects using project’s SD
  Proved difficult to understand
  Needs to be “PI terms”
PI vs. Reference Trend Line (0 = Industry Mean)
PI Std Deviation
-2.0
-1.5
-1.0
-0.5
0.0
0.5
1.0
Average Deviation Sigma
-0.41
-1.28
-0.91
-0.70
-0.41
-1.28
-0.91
-0.70
3Q04
1Q04
2Q04
4Q04
Performance Reporting

## Slide 12
1
10
100
1,000
Effective SLOC (thousands)
0
2
4
6
8
10
12
14
16
18
20
22
PI
-1sd
-2sd
+1sd
+2sd
PI vs Effective SLOC
Performance Reporting

## Slide 13
Quarterly Productivity Measures
Productivity
Adjusted PI
1
3
5
7
9
11
13
15
Avg. Adjusted PI
11.7
11.6
12.3
13.2
(Normalized)
(Normalized)
FY06Q1
FY06Q2
FY06Q3
FY06Q4
Performance Reporting

## Slide 14
Quarterly Productivity Measures
Duration
Adj. Days/KLOC
0
2
4
6
8
10
12
Avg. Days/KLOC
9.5
9.3
8.5
7.7
(Normalized)
(Normalized)
Effort
Adj. Hrs/KLOC
0
100
200
300
400
500
600
Avg. Hours/KLOC
464.1
491.8
447.1
365.7
(Normalized)
(Normalized)
Cost
DC&T $ / Eff SLOC (Phase 3 Cost/Efunit)
0
5
10
15
20
25
Avg. Cost ($) per Line of Code
17.7
19.0
15.8
12.4
(Actual)
(Actual)
Quality
Adj. Defects/KLOC
0
1
2
3
4
5
6
7
Avg. Defects/KLOC
6.0
6.3
6.0
4.0
(Normalized)
(Normalized)

## Slide 15
Lab vs Date of Full Operational Capability (FOC)
PI vs Date of Full Operational Capability (FOC)
6/03
9/03
11/03
1/04
3/04
5/04
8/04
10/04
12/04
2/05
4/05
7/05
9/05
11/05
1/06
3/06
5/06
FOC Date
5
7
9
11
13
15
Adjusted PI
Laboratory 6.1
FOC Date = 04/29/2005
Adjusted PI = 10.0
(Normalized)
Laboratory 5.4
FOC Date = 06/30/2004
Adjusted PI = 13.0
Laboratory 5.4.2
FOC Date = 12/31/2004
Adjusted PI = 8.0
Laboratory 6.2
FOC Date = 4/1/2006
Adjusted PI = 12.9
Performance Reporting

## Slide 16
Lab vs Date of Full Operational Capability (FOC)
Duration
6/03
11/03
3/04
8/04
12/04
4/05
9/05
1/06
5/06
FOC Date
1
3
5
7
9
11
13
15
Adj. Days/KLOC
Lab 5.4
7.2
(Normalized)
Lab 5.4.2
14.5
Lab 6.1
10.8
Lab 6.2
6.9
Effort
6/03
11/03
3/04
8/04
12/04
4/05
9/05
1/06
5/06
FOC Date
0
200
400
600
800
1,000
Adj. Hrs/KLOC
Lab 5.4
607
(Normalized)
Lab 5.4.2
812
Lab 6.1
737
Lab 6.2
677
Cost
6/03
11/03
3/04
8/04
12/04
4/05
9/05
1/06
5/06
FOC Date
0
10
20
30
40
50
Cost per Line of Code
Lab 5.4.2
$44.59
Lab 6.1
$14.91
Lab 5.4
$17.20
(Actual)
Lab 6.2
$15.10
Quality
6/03
11/03
3/04
8/04
12/04
4/05
9/05
1/06
5/06
FOC Date
0
2
4
6
8
10
12
14
Adj. Defects/KLOC
Lab 5.4
5.8
(Normalized)
Lab 5.4.2
6.7
Lab 6.1
12.7
Lab 6.2
3.6

## Slide 17
Determining Baseline PI for New Projects
  PI for new a project based on previous project
  Typical goal: 10% improvement
  Determine PI that would be required to achieve “Productivity +10%”
  Adjust PI for size estimate of new project
Estimating

## Slide 18
Import reference (completed) project into SLIM-Estimate
Note productivity of reference project
Add target percent improvement in productivity
Adjust PI until target productivity is displayed.
PI is the reference baseline PI for a new project
Adjust PI for estimated size of new project
Use SLIM-Estimate PI calculator to adjust for complexity, skill sets, etc.
Method

## Slide 19
Actual PI
Reference project productivity
Estimating

## Slide 20
Adjust PI until target productivity is reached
Estimating

## Slide 21
Adjust PI
Calculate Baseline PI for New Project
  Enter size and PI of reference project
  Enter estimated size of new project
180,534
Enter Size of Estimated Project:
Enter Size of Reference Project:
98,000
Enter PI of Reference Project:
15.30
Equivalent PI for 98,000 M14SLOC is:
14.44

## Slide 22
PI vs Effective SLOC
1
10
100
1,000
Effective SLOC (thousands)
0
5
10
15
20
25
30
35
PI
Adjust PI
Starting with PI of reference project…
…adjust PI until target productivity is reached…
…calculate PI for estimated size of new project
Use PI Calculator to adjust for complexity, skill sets, etc.

## Slide 23
Project Roll-up
Project “Roll-up” for Scorecard Reporting
  Independent, separately estimated projects of a Release
  Needed a method of reporting overall status on “Scorecard”

## Slide 24
Project aggregated in SLIM-Estimate
  Sum of projects: SLOC, Peak Staff, REQ
Project Roll-up

## Slide 25
Project aggregated in SLIM-Control
  Custom Plan: Sum of all plans
Project Roll-up

## Slide 26
Feature-level SLIM
  Product Development “Feature Teams”
    Development, QC, Tech Pubs
  Issues Tracking/Measuring in SLIM
    Not necessarily a continuous effort
      What if start of QC testing is delayed?
    How to account for rework effort occurring after main development, prior to customer release
      Redefine Phase 4 to capture rework?
        When did Phase 3 really end?
Feature-level
SLIM

## Slide 27
0
200
400
600
800
1000
1200
1400
1600
1800
2000
May-03
Jun-03
Jul-03
Aug-03
Sep-03
Oct-03
Nov-03
Dec-03
Jan-04
Feb-04
Mar-04
Apr-04
May-04
Jun-04
Jul-04
Aug-04
Sep-04
Oct-04
Nov-04
Dec-04
Jan-05
Feb-05
Effort (person hours)
Actual
SLIM
Actual vs. SLIM-Estimate
Feature-level
SLIM

## Slide 28
Feature-level
SLIM
0
100
200
300
400
500
600
700
Oct-03
Nov-03
Dec-03
Jan-04
Feb-04
Mar-04
Apr-04
May-04
Jun-04
Jul-04
Aug-04
Sep-04
Oct-04
Nov-04
Dec-04
Jan-05
Feb-05
Effort (person hours)
Actual
SLIM
Actual vs. SLIM-Estimate

## Slide 29
Feature-level
SLIM
Actual vs. SLIM-Estimate
0
100
200
300
400
500
600
700
Jun-03
Jul-03
Aug-03
Sep-03
Oct-03
Nov-03
Dec-03
Jan-04
Feb-04
Mar-04
Apr-04
May-04
Jun-04
Effort (person hours)
Actual
SLIM

## Slide 30
Feature-level
SLIM
Actual vs. SLIM-Estimate
0
50
100
150
200
250
Jun-04
Jul-04
Aug-04
Sep-04
Effort (person hours)
Actual
SLIM

## Slide 31
PI vs Effective SLOC
0.1
1
10
100
1,000
Effective SLOC (thousands)
-5
0
5
10
15
20
25
PI
Feature-level
SLIM
“Derived” Projects (features)
  “Fit” with our existing projects (so far)
Releases
Features

## Slide 32
What Needs to be Done
  Tune Phase Overlap & Ratio
  Tune Milestones
  Tune the Shopping Cart
    More accurate size estimates
    Feedback from this exercise would help in the shift to thinking in size as opposed to effort