## Slide 1: Agile Management: Software Release Increments
Increment
Software Release
Jim Greene QSM Ltd www.qsmuk.com.
Tel: 44-(0)207-603-9009 j.greene@qsmuk.com
(R-Reference)
NASA strategy "faster, better, cheaper"
Notes: Managing Software Release Increments
“NASA's recent philosophy of conducting more "faster, better, cheaper" space missions instead of a few large ones appears sound and should continue to be a part of future planning, experts on the panels said. However, they said, this approach has limits and many of these projects need to be more closely managed to assure success.”
Many software development organisations are faced with the same challenge: moving from delivering large releases to a series of release increments. The challenge is to deliver features on time, within budget and with high quality. Like NASA “these projects need to be more closely managed to assure success.”
To be successful it is necessary to quantify how much software can be developed consistent with the time and staff available as well as the process productivity of the development team.
This is just the start. Once a realistic estimate is made that meets the constraints then the on-going development needs to be carefully managed. Progress must be made continuously visible to give confidence that delivery will be as planned. Regular forecasts to complete must be made using actual progress reported to date.
Often change requests are inevitable. These impact the outstanding development plan. A solution is needed to assess their impact and allow informed updates to be made to the plan. Likewise informed decisions must be made if slippage is detected. It may be necessary to extend the plan or reduce the features to meet the increment delivery commitment. At delivery there must be confidence and proof that the software is highly reliable.
Incremental releases are usually eagerly awaited by customers. For their part customers are motivated similarly to manage supplier’s developments. The steps outlined below are capable of being managed by customer purchasing organisations by asking for and using the supplier data described in this paper. (Ref. 7 )

## Slide 2: Managing Software Release Increments: the challenges
How many features are practical within the constraints: ► Time? ► People? ► Reliability? ► Risks?
Increment
Software Release
How to make progress visible and manage: ► Change Requests? ► Slippage? ► Delivery on time with high quality?
Notes: In summary the challenge is to estimate and set up a baseline plan consistent with:
The size and uncertainty of the features
The time available
The staff available
The development process productivity
The challenges continue as development progresses. Actual progress against the plan has to visible and reported typically each week (NASA: “closely managed “). At any point during development it must be practical to:
Detect risks to the development
Make informed management decisions if slippage is detected
Assess change requests and investigate re-planning options
Ensure delivery is made with high quality i.e. minimal remaining defects
Next we provide an overview of the steps to meet the release increment management challenges and then describe each step in more detail.

## Slide 3: Managing Release Increments The Steps
Release increment
Step 1 Benchmark
Step 2 Size the features
Step 3 Increment baseline
Step 4 Increment control
Step 5 Increment reliability
Step 6 Update benchmark
Notes: Managing Release Increments: The Key Steps
Slide 3 summarises the steps . The first step is to benchmark the development organisation. Benchmarking uses basic data from completed projects to quantify the process productivity of teams within the development environment. The minimum benchmark data is the development time, effort and size. Purchasing asks for this data to benchmark and build a supplier database.
It is then practical to determine the total size of the software that can be developed within the increment constraints of time, available staff and process productivity. In parallel the features in the increment are identified. Each feature is sized in terms of the minimum, most likely and maximum statements. Each feature is prioritised so that an evaluation of alternative sizes and their uncertainty is possible to decide how many features and how much software is feasible to stay within the increment development constraints. The size range uncertainty allows risk assessment when estimating the increment development plan.
Next the increment plan is estimated consistent with the constraints and feature size. This plan forms the baseline for tracking, controlling and reporting progress. Increment development control collects weekly progress data and performs variance analysis against the baseline plan. Each week the progress is assessed against key indicators. If slippage is determined then a forecast is made of the outstanding effort and time to complete the increment. Any change requests are first evaluated to determine their potential impact. Informed decisions are made to accept or postpone the change request depending on its priority.
As delivery approaches the defect data reported is used to forecast the outstanding defects and the expected final quality. Delivery is made when the required quality is achieved. At completion the time, effort, size and defects are used to update the benchmark database. This includes the process productivity achieved by the supplier. For a development group any improvement in process productivity is quantified and the commercial benefit determined. For purchasers the productivity measure enables an evaluation of supplier process improvement over time.

## Slide 4: Step 1 Release benchmark
Determine development team process productivity Completed development data : Main development phase
Project Summary Report : Supplier Major Releases
Project Name
Organization
Major Release Size
(Statements)
Development
Effort (Person
Months)
Development
Time (Months)
Average
Development Staff
(People)
QSM Process
Productivity
Index (PI)
Industry
Development
End Date
MAJOR RELEASE 1
SUPPLIER
540,000
1,600.00
23
70
17
Electronics
April 2002
MAJOR RELEASE 2
SUPPLIER
930,000
2,750.00
25
110
18
Electronics
February 2003
MAJOR RELEASE 3
SUPPLIER
252,000
900
12
74
18
Electronics
July 2003
AVERAGE
574,000
1,750
20
85
18
Benchmark results: Completed releases are: ► Large >250,000 statements ► Long development time ~ 12/25 months ► Achieve a high process productivity index ~ 18
Requirement : Release increment every 6 months: ► How much software can be developed? ► Constraints : 6 months, productivity index 18, maximum staff 85
(R1/R2)
Notes: Step 1 Release Benchmark
Benchmarking begins by getting data on recently completed releases. Time, effort and size are collected for the main development phase. The table above illustrates the benchmark data. Note that these release are very large, at least 250,000 statements, take between 1 and 2 years to develop and use teams that average around 85 people.
The benchmark data allows the process productivity of the development teams to be calculated. Purchasing organisation request this data from suppliers to build a benchmark database to evaluate and negotiate new proposals.
With this information the next step is to quantify how much software is practical within development constraints : increment delivery within 6 months, maximum of 85 staff available and the quantified process productivity index (PI =18).

## Slide 5: Step 2 How much software can be produced within constraints?
Maximum 85 staff
6 months
78400 statements
(R3-1)
Inputs
Output
Notes: Step 2: How much software within the constraints?
This question is answered by inputting the parameters time, staff and process productivity (as shown in slide 3) to the software lifecycle model (Ref. 7). In this case inputting the development time 6 months, maximum staff 85 and process productivity index PI = 18 yields a size of around 78,000 statements.

## Slide 6: Step 3 Estimate increment features : priorities and size
30
97233
1726
92054
to
102413
Include features
1
with Priority >=
Number of Features
Expected Total:
Sigma:
99% Range:
2
with Priority >=
Include features
77006
to
67728
99% Range:
1546
Sigma:
72367
Expected Total:
20
Number of Features:
Size limit 78400 statements
Too large
(R3-2)
Size OK
Size range
Feature Priority
Notes: Step 3: Which Features can be built?
The next action is to quantify and prioritise the increment features. Slide 6 illustrates how each feature is estimated in terms of the minimum, most likely and maximum statements. Each feature is prioritised. In the example high priority features are 5; low priority 1.
The mean estimated size and uncertainty for all the features yields a result of around 97,000+/- 1,700 which is above the limit of 78,000 statements. The size range estimate for priority 2 features and above is around 73,000 +/- 1500 and is within the maximum allowed, 78,000.
Hence a confident size estimate is made of the features consistent with the increment development constraints. Here the size of all priority 2 features and above is used as an input to estimate the baseline development plan. This plan is set up anticipating there may be problems of slippage or change requests during development. The top priority features are developed first followed by each lower priority set of features. This prioritised incremental development provides flexibility to respond to slippage and change requests as illustrated next.

## Slide 7: Step 3 Increment development estimate : the baseline plan
Inputs: PI 18 Increment size range 72367+/- 1546 Time 6 months Peak staff 85
(R3-3)
20
72367
1546
67728
to
77006
Include features
2
with Priority >=
Number of Features:
Expected Total:
Sigma:
99% Range:
Notes: Step 3: The Baseline Plan
The baseline plan is structured anticipating there may be problems of slippage or change requests during development. The top priority features are developed first followed by each lower priority set of features. This prioritised incremental development provides flexibility to respond to slippage and change requests as illustrated in slide 8.

## Slide 8: Step 4 Release increment control: report weekly progress data
Milestones: Feature Priority Start-FP5S End-FP5E etc.
Feature and total size developed to date
Defects: Critical; Major; Minor
Integration/Regression tests: Number :Start-ITS End-ITE etc.
Features P5
Features P4
Features P3
Integration Tests
Regression Tests
FP5S
FP5E
FP4S
FP4E
FP3E
FP3S
ITS
MILESTONES
ITE
RTS
RTE
STAFF
6 MONTHS
Features P2
FP2S
FP2E
(R4-1)
Notes: Step 4: Increment Control: Increment Milestones and Test Plans
An illustration of the detailed feature planning is shown in slide 8. Major milestones are set corresponding to the start and end of each priority block of features. Start and end dates are set for the integration and regression tests as the baseline plan is finalised. These form part of the progress reporting milestones.
Equally the size in estimated statements of each priority block is used to set up and track development progress goals as are the planned number of integration and regression tests.

## Slide 9: Step 4 Increment control: Weekly progress assessment and report
Plan/Actual/Forecast
Track Tests
Track Statements
Track Staff/Milestones
Assessment report (OK) after 8 weeks development
(But integration tests slipping slightly)
(R4-2/3)
Each week report progress
30/07/2004
Notes: Step 4: Increment Control
Each week progress data is collected and used to detect if variance is occurring against these baseline plan goals. A high level weekly progress report sets out results from the progress data versus the plan to determine variance and highlight risk..
The adjacent slide shows the position at week eight. Each progress indicator is assessed. Here all the faces are smiling except integration test progress where there may be cause for concern.

## Slide 10: Step 4 Increment control “What If” change request?
Evaluate impact : Negotiate plan
New Priority 1 Feature estimated size 4000 statements : Impact analysis at week 8 : Slippage forecast 4 weeks. Alternatives: A) Revise plan
B) Drop Priority 2 Features- reduce by 4000 statements
Plan/Actual/Forecast
Impact increased tests
Impact increased statements
(R4-3)
(New feature)
Notes: Step 4: Here comes the Change Request!
At week eight a change request arrives. The size of the additional features is estimated at around 4000 extra statements. This additional size is added to the current size and the position in the development used to forecast the impact. Advanced forecasting algorithms take in to account the current position in the development using confidence indicators from the progress data to weight the forecast.
The result shown in slide 10 indicates there will be a slippage of around 4 weeks if the request is accepted. Management must make a decision either to revise the outstanding plan or drop lower priority 2 features to maintain the baseline plan.
This is straight forward since each low priority feature is sized and a decision is quickly made regarding what features may be dropped.

## Slide 11: Step 4 Increment control: “What If” slippage detected?
Forecast-using progress data to-date
Track Tests
Track Statements
Integration tests and statements slipping significantly
Assessment after 10 weeks development
4 weeks slippage
(R4-3)
Each week report progress
30/07/2004 06/06/2004 20/08/2004
Notes: Step 4: What about slippage?
Even the best estimate and baseline plan may be faced with slippage during development. If this starts to occur then the prioritised features allow informed decisions to either reduce size by dropping low priority release feature or revise the plan.
In slide 11 slippage is detected at week 10 due to software production and integration tests falling behind schedule. The release objectives can still be met by dropping lower priority features. This reduces the software size and the number of integration and regression tests and the project is back on track in week 11 as shown in slide 12.

## Slide 12: Step 4 Increment Control: Slippage : Action reduce size Drop priority 2 features (~23K)
Plan/Actual/Revise Forecast
Track Tests
Track Statements
Integration tests and statements back on track
Assessment after 11 weeks development
Reduce: Size 73K > 50K Integ. Tests : 350 >300 Regress. Tests 750 > 650
(R4-3)
30/07/2004 06/06/2004 20/08/2004 03/09/2004

## Slide 13: Step 5 Increment reliability : record-forecast defects
Weekly defect data recorded.
Use to forecast outstanding defects
Delivery when critical/major defects ~ 0
Cumulative defect curve smoothes out rate curves
Total
Critical
Major
(R4-3/R5)
Notes: Step 5: Forecasting and Ensuring Delivery Quality
Each week defect data is collected broken down in to categories: critical, major, minor.
Rate data for defects varies depending on the test cases exercised each week. Control bounds are set to turn on traffic light indicators, slide 13, if the rates go outside the bounds.
Cumulative defect data analysis smoothes out the fluctuating rate information and provides a sound forecast of remaining defects. This data is used as shown in slides 13 and 14 to forecast the outstanding defects and the time between defects (Mean Time to Defect MTTD). Delivery is made when critical and major defects are zero (Ref. 5).

## Slide 14: Step 5 Release increment delivered reliability
Critical and major defects 0
Total defects
High Mean Time between Defects ~ 30 days (MTTD)
Actual defects reported each week :critical; major; minor
Use to forecast remaining defects in each category
Delivery when critical & major defects ~ 0
(R4-3/R5)

## Slide 15: Step 6 :Completed increment update benchmark database
Increment
(R2)
Software Release
Complete project history
Every week development history
30/07/2004 06/06/2004 20/08/2004 03/09/2004
30/07/2004 06/06/2004 20/08/2004 03/09/2004
Notes: Step 6: Update the Benchmark Database
At completion a full history exists of the weekly progress data together with the management reports. This data is used to update the benchmark database.
Development groups use the result to determine if their process productivity has improved. Evidence of improvement enables the commercial benefits to be calculated compared to earlier productivity values. Recording this information for all completed projects allows the Return on Investment to be demonstrated through process improvement initiatives such as CMM/CMMI SE/SW.
Purchasers add to their database of supplier performance to aid informed supplier negotiation on future developments. They benefit by quantitatively managing suppliers. These quantitative purchasing processes meet major CMMI Acquisition Management requirements..

## Slide 16: Step 6 Update benchmark database
Increment size
Developed in 6 months
Process productivity improved
Calculate ROI due to improvement initiatives (CMM/CMMI)
Increment
(R4)
Software Release
Project Name
Organization
Major Release
Size (Statements)
Development
Effort (Person
Months)
Development
Time (Months)
Average
Development
Staff (People)
QSM Process
Productivity
Index (PI)
Industry
Development
End Date
MAJOR RELEASE 1
SUPPLIER
540000
1600
23
70.13
16.6
Electronics
04/2002
MAJOR RELEASE 2
SUPPLIER
930000
2750
25
110.57
17.7
Electronics
01/2003
MAJOR RELEASE 3
SUPPLIER
252000
900
12
73.61
17.7
Electronics
07/2003
RELEASE INCREMENT
SUPPLIER
76000
325
6
53.84
18.1
Electronics
12/2004
AVERAGE
449500
1394
16
77
18
Notes: Slide 16 shows the results from the incremental strategy. Development time is 6 months with the final increment size 76,000 statements. The process productivity has improved to 18.1 compared to the earlier larger releases.

## Slide 17: Managing Software Release Increments
SEI core data (R6) is used to:
Ensure the increment estimate is consistent with ► Features, priorities and size ► Process productivity ► Time ► Staff
Track, report progress and identify risks
Manage change requests: informed re-planning decisions
Detect slippage and re-plan
Ensure each increment delivered with high quality
Measure process productivity improvement
Increment
Software Release
Notes: Increment Release Conclusions
The example shown here demonstrates the practicality of managing release increments to achieve faster delivery on-time, within budget and at a high level of reliability. Paraphrasing NASA “"faster, better, cheaper".
Slippage and change requests are anticipated by scheduling feature blocks prioritised within the overall development plan. Management is then in the position to make practical decisions as and when these occur.
Analysis of high level progress data ensures the management is always informed about the status in the project on a week to week basis. Just like NASA “projects need to be more closely managed to assure success.”
The weekly data is recorded and shows if there is significant variance versus the baseline development plan. This data provides a complete history to enable an informed review to be held at project completion. Lessons learned are used by suppliers and purchasers alike to understand the key factors impacting software development. Positive factors are capitalised on while problems are identified to avoid in future developments.
Both suppliers and purchasers benefit at all development stages with the quantified data that leads to realistic commitments, control and delivery of the release increments.

## Slide 18: Are Increments "faster, better, cheaper“?
Faster?- yes, less risk of change requests but fewer features
Better?-fewer features, less software = fewer defects, higher quality
Cheaper?- take care to understand the cost drivers
  Driver 1 Size
  Driver 2 Team Process Productivity PI
  Driver 3 Planned development time
Increment
Software Release
Notes: However the crunch question is: Are release Increment developments “faster, better, cheaper”? The get out is to say that each criteria depends on understanding the impact of the increment development cost drivers. Each criteria needs to be qualified.
Faster: clearly smaller increments require shorter development timescales; the trade off is less risk of change requests but fewer features are delivered.
Better: fewer features results in less software which means potentially fewer defects and higher delivered quality.
Cheaper: here care is needed based on an informed understanding of the impact of the three drivers that determine effort and cost.
Cost driver 1: size-fewer features, reduced size equals less cost.
Cost driver 2: development process productivity. In the case study a PI of 18 is achieved. Improving to a PI of 19 while keeping the same size and maximum staffing at 85 means effort is reduced by 5 person years and time reduces from 6 months to 5.5 months
Cost driver 3: planned development time is a major factor that determines cost and quality. Keeping the same inputs as the case study but extending the planned time by one month to 7 months reduces the effort by 12 person years and reduces the peak staffing from 85 to 40 people!
So the answer to the question is a qualified yes. The qualification is you must be aware and manage the cost drivers especially the planned development time.

## Slide 19: Cheaper?- manage the drivers!
  Driver 1 Size- reduced size equals less cost
  Driver 2 Process Productivity PI: improve PI from 18 to 19, same size and 85 staff-
    benefit 5 person years less effort,
    time reduced from 6 months to 5.5 months
  Driver 3 Planned Time: PI at 18, same size extend development time by 1 month- now 7 months
    benefit 12 person years less effort
    staff reduced from 85 to 40!
Increment
Software Release
Notes: Cost driver 1: size-fewer features, reduced size equals less cost.
Cost driver 2: development process productivity. In the case study a PI of 18 is achieved. Improving to a PI of 19 while keeping the same size and maximum staffing at 85 means effort is reduced by 5 person years and time reduces from 6 months to 5.5 months
Cost driver 3: planned development time is a major factor that determines cost and quality. Keeping the same inputs as the case study but extending the planned time by one month to 7 months reduces the effort by 12 person years and reduces the peak staffing from 85 to 40 people!
So the answer to the question is a qualified yes. The qualification is you must be aware and manage the cost drivers especially the planned development time.

## Slide 20: Contact : j.greene@qsmuk.com References
Ref 1 Software Benchmarking: Common Sense and Rocket Science Using the SEI Core Measures. J. Greene QSM Ltd. (SEI Measurement/Metrics http://seir.sei.cmu.edu)
Slide :R2 SLIM-Metrics*
Slide :R3 SLIM-Estimate* R3-1 Design To Size R3-2 Feature sizing R3-3 Estimate
Slide :R4 SLIM-Control* R4-1 Plan R4-2 Actual R4-3 Forecast
Ref. 5 Avoiding the Premature Delivery of Software J. Greene QSM Ltd. (SEI Measurement/ Metrics http://seir.sei.cmu.edu)
Ref. 6 The SEI Core Measures Anita D. Carleton, Robert E. Park and Wolfart B. Goethert The Journal of the Quality Assurance Institute July 1994
Ref. 7 Industrial Strength Software: Effective Management Using Measurement, Lawrence H. Putnam and Ware Myers, IEEE Computer Society Press, Los Alamitos, CA, 1997, 309 pp.
*Quantitative Software Management QSM Software Lifecycle Management - SLIM tool