## Slide 1: QSM Off-shore Benchmark
Off-shore
Software Benchmark
Jim Greene QSM Ltd www.qsmuk.com.
Tel: 44-(0)207-603-9009 j.greene@qsmuk.com
Notes: Managing Software Release Increments
“NASA's recent philosophy of conducting more "faster, better, cheaper" space missions instead of a few large ones appears sound and should continue to be a part of future planning, experts on the panels said. However, they said, this approach has limits and many of these projects need to be more closely managed to assure success.”
Many software development organisations are faced with the same challenge: moving from delivering large releases to a series of release increments. The challenge is to deliver features on time, within budget and with high quality. Like NASA “these projects need to be more closely managed to assure success.”
To be successful it is necessary to quantify how much software can be developed consistent with the time and staff available as well as the process productivity of the development team.
This is just the start. Once a realistic estimate is made that meets the constraints then the on-going development needs to be carefully managed. Progress must be made continuously visible to give confidence that delivery will be as planned. Regular forecasts to complete must be made using actual progress reported to date.
Often change requests are inevitable. These impact the outstanding development plan. A solution is needed to assess their impact and allow informed updates to be made to the plan. Likewise informed decisions must be made if slippage is detected. It may be necessary to extend the plan or reduce the features to meet the increment delivery commitment. At delivery there must be confidence and proof that the software is highly reliable.
Incremental releases are usually eagerly awaited by customers. For their part customers are motivated similarly to manage supplier’s developments. The steps outlined below are capable of being managed by customer purchasing organisations by asking for and using the supplier data described in this paper. (Ref. 7 )

## Slide 2: QSM Off-shore Benchmark
Challenge – only part of QSM main build performed off-shore
Off-shore developments very large, short timescales, large teams
How to determine off-shore Process Productivity Index up to delivery on-shore?

## Slide 3: Solution: Determine Off-shore In Process PI
Using Off-shore Plan Data
And
Actual Off-shore Progress Data
SLIM-Control

## Slide 4: On-shore/Off-shore software phases : an overview
Requirements
Software Development: Detailed design/code-unit test
Integration/System Test
Responsible
On-Shore Features
Responsible
Off-shore
Responsible
On-shore
QSM Main Build
Worldwide
3 Continents
Worldwide

## Slide 5: On-shore/Off-shore software phases : The Benchmark Challenge
Requirements
Software Development: Detailed design/ code-unit test
Integration/System Test
Responsible
On-Shore Features
Off-shore
On-shore
QSM Main Build
Data : Plans/Progress data/defects
No data
No data

## Slide 6: Software Development: “V” Diagram
On-shore Feature Specification /Component Mapping
On-shore Component Integration validation
Component Detail Design.
Validate Unit Test Code
Off-shore
Data:
PLAN ACTUAL
Input to SLIM-Control

## Slide 7: Input data (weekly example)
Milestones
Planned- e.g. start/end dates component 1
Actual- e.g. start/end date component 1
Actuals
Staff
Defects
Component 1 build

## Slide 8: SLIM-Control-Progress Data Analysis
Number of Data Points
Goodness of fit
Forecast
Development
Time
Weight Forecast use to calculate In-progress PI

## Slide 9: SLIM-Control Compute In Progress PI
In-progress Process Productivity Index to on-shore handover

## Slide 10: Time Plan : Actual : Forecast
Plan Blue : Actual Red : Forecast White
Size:
860,000 statements
100 staff
4 months

## Slide 11: Plan/Actual Forecast PI
Plan PI = 26.5
Actual PI = 24.7
at On-shore delivery
MBI ~ 7/6
High
Time
Pressure

## Slide 12: Issues: In-Progress PI: What happens at handover? Best case/ Worse case
Best case at Off-shore handover
  Few defects remain
  Less on-shore work- short time/low effort
  Final End to End PI not lower
Worse case at Off-shore handover
  High defect levels
  High on-shore work- long time/high effort
  Final End to End PI lower

## Slide 13: Off-shore Benchmark Results
Proof of concept- verified on 20 pilot projects: across 3 continents
Consistent benchmark results
Data extended to include On-shore integration/system test
Current Database (QSM Data Manager) 200 projects

## Slide 14: Questions? Please contact
Jim Greene
E-mail j.greene@qsmuk.com
Tel: France 00-33-(0)140431210 UK 00 –44-(0)20-7603-9009
Notes: <number>
<footer>
<header>
<date/time>