## Slide 1: Larry Putnam Initial Research Circa 1975
Notes: Kate got a call wanting to know about my original research work, the data, the curve fits, the statistical fits of algorithms. She called me to see if I still had anything. I told her No; couldn’t remember where it might be. Three weeks ago I was clearing out some stuff in my attic and came across a great deal of the early stuff – the computer printouts of curve fits, the early estimators, the vu-graphs explaining it. I looked it over and thought it was fascinating So, I’m going to take you back about 30 years and show where things came from, what was good, and what has lasted.

## Slide 2: Background
Time Frame 1975
SIDPERS $10 Million Budget Loss
Discovery of Norden-Rayleigh Equation
Research to Discover the Rayleigh Parameters (Time and Effort)
Who had some data and what did it look like?
Notes: How I got in the business with SIDPERS

## Slide 3
This is the project that I Lost $10 Million on
Notes: Rayleigh curve fits well. Straight line budget projections got me in trouble.

## Slide 4
Determining the lifecycle effort (K) from the number of files and application programs in the system (sizing metrics)
Manpower Build up
Parameter
Notes: Detrmiing the life cycle effort from the number of application programs and number of files a system had.

## Slide 5
The Original Army Data Set (19 Good projects)
Homogenous Data Set
  Same organization
  Same application type
  Same tooling
  Complete data (size-time-effort)
Size Metrics
Man was I LUCKY !
Notes: Some good data from the Army Computer Systems Command

## Slide 6
These are possible equations that would have to intersect (any 2) to provide the parameters for time and effort (K and td)
(X1,X2,X3 are Size Metrics)
Notes: 7 equations I did curve fitting with. All of these involved files, reports and application programs as the sizing metrics.

## Slide 7
Matrix math to solve simultaneous equations
5 equations relating the number of reports and application programs to time and effort….The parameters needed to generate the Rayleigh staffing model
Goodness of Fit
Notes: Simultaneous equation solving to get the coefficients of the equations.

## Slide 8
Mathematical solution
of all 7 equations
Software Equation
Early Version
Manpower
Buildup Index
Notes: Some graphical curve fitting of the equations. This is a log-log plot of Effort v. Schedule – the parameters of the Rayleigh equation.
We use at least four of these in the SLIM solution today

## Slide 9
Milestone determination based on the average of these 5 Army Systems

## Slide 10
End Product Estimate (Schedule, Effort and Milestones)
Notes: The Rayleigh model with schedule, Life Cycle effort and milestones superimposed.

## Slide 11: Key Thoughts
Rayleigh Model is excellent model of human design processes
Software equation captures the time effort trade-off relationship
The algorithms have withstood the test of time
We must be close to the fundamental behavior of software development